## Instructions
Instructions for use of Integrated Plan Work Plan and Monitoring Tool
Purpose:
This Integrated Plan and Monitoring template provides jurisdictions with a dynamic tracking tool to centralize and operationalize their Integrated Plan. This is considered a "living document" that should be used to organize strategies with corresponding goals, identify data sources, delegate tasks, monitor and track progress toward goals, and support reporting.
How to use:
Jurisdictions should identify the goals and objectives outlined in the Integrated Plan and operationalize each objective with specific and measurable strategies. This information, along with measure definitions, data sources, and responsible individuals should be recorded in the respective columns. When possible, provide updates related to progress or notes relevant to the execution of the strategy. This worksheet is a suggested template and can be submitted as Section V in the Integrated Plan submission. This worksheet can also be used as a "living document" to assist in achieving the steps outlined in Section VI: Integrated Planning Implementation, Monitoring, and Jurisdictional Follow-Up.
Goal #:
Goal correspond to goals established in the 2027-2031 Integrated Plan.
Objectives | National Goals | EHE Strategy | Activity/ Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2031) | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
Objectives are actionable components of the goal and can include activities such as data gathering, programmatic activities, and meeting coordination. Multiple objectives can be included if applicable to the strategy. | Identify corresponding National goal(s). | Identify corresponding EHE strategy (i.e., Diagnose, Treat, Prevent, Respond) | Details a specific and measurable task, activity, or data point that operationalizes the objective. | Numerical value, product, or meeting convening demonstrating outcomes related to the activity. | The initial year for which future progress/outcomes will be measured against. | The initial value for which future progress/outcomes will be measured against. | The target value/outcome for the end of the IP cycle. | Where the data or outcome is tracked/stored. | Key partners involved in data collection and/or service delivery. | Office or position overseeing the collection and/or reporting of data related to the activity. | Office or position overseeing the execution/coordination of the activity. | Current state of the activity; identify any implementation barriers. | Detail information relevant to the implementation of the activity. | Details progress on activity as it relates to the overall objective; include numerical values and concrete outcomes when possible.

## IP Workplan and Monitoring Exam
Integrated HIV and Prevention and Care Plan Work Plan and Monitoring Table, 2027-2031
Goal 1: Example: Diagnose all people with HIV as early as possible.
Objectives | National Goals | EHE Strategy | Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2031) | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
To increase the number of HIV tests conducted by 20% within the jurisdiction by 2031. | 1.2, 1.4, 2.4 | Diagnose | Increase capacity of health care delivery systems to offer routine testing in 20 ERs, acute care settings, etc. | # of HIV tests |  | 15000 | 18000 |  | RWHAP Part A recipient, RWHAP Part B recipient, EHE recipient, CDC recipient | HIV Epidemiologist and Data Manager | HIV Division Manager | In Progress | Data pulled quarterly and reported by HIV Epidemiologist & Data Manager, reported to Planning Council by HIV Division Manager. | 3% increase in number of HIV tests relative to baseline year.
|  |  |  | # of newly identified persons with HIV | 2027 | 600 | 720 | Epi Database
To increase the number of HIV tests conducted by 20% within the jurisdiction by 2031. | 1.2, 1.4, 2.4, 3.4 | Diagnose | Plan and develop a wide dissemination of self-testing kits through system partners across the jurisdiction to improve access for testing. | # of HIV self-test kits |  | 15000 | 18000 | Epi Database | RWHAP Part A recipient, RWHAP Part B recipient, EHE recipient, CDC recipient | HIV Epidemiologist and Data Manager | HIV Division Manager | Delayed, rapid test protocol pending department approval, distribution planned for Q3 | Data pulled quarterly and reported by HIV Epidemiologist & Data Manager, reported to Planning Council by HIV Division Manager | None
|  |  |  | # of newly identified persons with HIV | 2027 | 600 | 720
Goal 2: Example: Treat HIV timely and effectively.
Objectives | National Goals | EHE Strategy | Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2031) | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
To engage and provide access to care for 400 people with HIV by 2028. | 2.5, 3.4, 4.1, 5 | Treat | Identify and address mental health barriers for people who have never engaged in care or who have fallen out of care by partnering with mental health providers | # of newly identified persons with HIV linked to care within 30 days |  | 600 | 720 | Epi Database | RWHAP Part A recipient, RWHAP Part B recipient, EHE recipient | HIV Epidemiologist and Data Manager | RWHAP Part A recipient, RWHAP Part B recipient, EHE recipient | In progress | Outreach to 8 regional mental health providers. | Standing meeting topic for Planning Council meetings, presentations planned from mental health providers.
|  |  |  | # of persons with HIV identified as not in care linked to care within 30 days | 2027 | 500 | 780
To engage and provide access to care for 400 people with HIV by 2028. | 2.2, 2.3, 3.4 | Treat | Develop and implement at least one effective, evidence-based, or evidence-informed interventions that improve retention in care | # of newly identified persons with HIV linked to care within 30 days |  | 600 | 800 | Epi Database | RWHAP Part A recipient, RWHAP Part B recipient, EHE recipient | HIV Epidemiologist and Data Manager | RWHAP Part A recipient, RWHAP Part B recipient, EHE recipient | Implementation pending planning council decision. | Planning council requires additional training on HIV syndemics with a focus on mental health interventions. | Scheduled for review at Q2 Planning Council meeting.
|  |  |  | # of persons with HIV identified as not in care linked to care within 30 days | 2027 | 500 | 700
Goal 3: Example: Prevent new HIV transmissions.
Objectives | National Goals | EHE Strategy | Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2031) | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
To increase access to PrEP by 20% for people and communities disproportionately impacted by HIV by 2031. | 1.3, 1.4 | Prevent | Increase number of providers trained each year by 10% to prescribe PrEP | # of providers trained | 2027 | 750 | 1125 | Epi Database | RWHAP Part A recipient, RWHAP Part B recipient, EHE recipient, CDC recipient | HIV Division Manager | HIV Division Manager | In progress | Curriculum provided by TA provider. | Launched PrEP provider Community of Practice, focusing on new prescribers.
To increase access to PrEP by 20% for people and communities disproportionately impacted by HIV by 2031. | 1.3, 1.4, 3.2 | Prevent | Increase PrEP prescriptions among people and communities disproportionately impacted by HIV to reduce health disparities | # of prescription initiations for PrEP | 2027 | 8000 | 9600 | Epi Database | RWHAP Part A recipient, RWHAP Part B recipient, EHE recipient, CDC recipient | HIV Epidemiologist and Data Manager | HIV Division Manager | In progress | Data Management Team is building report with data stratified by people and communities disproportionately impacted by HIV | Year 1 update to be provided at the end of Q4.
Goal 4: Example: Respond quickly to potential HIV clusters and/or outbreaks.
Objectives | National Goals | EHE Strategy | Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2031) | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
To develop a Cluster and Outbreak Detection and Response (CDR) Plan that can be executed effectively by 2028. | 4.2, 4.4 | Respond | Identity and engage all key collaborators in the plan development process, including people with lived experience and those with certain risk factors for acquiring HIV | Completion of CDR Plan | 2027 |  |  | CDR Plan | CDC Recipient (HIV Prevention Coordinator), CDR Committee | HIV Prevention Coordinator | HIV Prevention Coordinator | In progress |  | Recruitment ongoing, 6 partners identified as of Q1. Meeting scheduled for Q3.
To develop a Cluster and Outbreak Detection and Response (CDR) Plan that can be executed effectively by 2028. | 4.2, 4.4 | Respond | Convene existing communities of practice to share outbreak best response practices and known gaps to guide development and key strategies in the plan | Completion of CDR Plan | 2027 |  |  | CDR Plan | CDC Recipient (HIV Prevention Coordinator), CDR Committee | HIV Prevention Coordinator | HIV Prevention Coordinator | In progress |  | First convening occurred Q1, initial report to be released Q2.

## IP Workplan & Monitoring Templa
Integrated HIV and Prevention and Care Plan Work Plan and Monitoring Table, 2027-2031
Goal 1:
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15
Objectives | National Goals | EHE Strategy | Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2031) | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
Goal 2:
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15
Objectives | National Goals | EHE Strategy | Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2031) | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
Goal 3:
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15
Objectives | National Goals | EHE Strategy | Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2031) | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
Goal 4:
Objectives | National Goals | EHE Strategy | Activity/Performance Measure | Measure Definition | Baseline Year | Baseline Value | Year 5 Targets (2031) | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes