## Instructions
Instructions for use of the Integrated HIV Prevention and Care Plan Work Plan and Monitoring Table Template
Purpose:
This Integrated HIV Prevention and Care Plan Work Plan and Monitoring template provides jurisdictions with a dynamic tracking tool to centralize and operationalize their Integrated Plan. This is considered a "living document" that should be used to organize goals, objectives, and strategies; identify data measures and sources; delegate tasks; monitor and track progress toward goals; and support reporting.
How to use:
Jurisdictions should identify the goals and objectives outlined in the Integrated Plan and operationalize each objective with specific and measurable strategies. This information, along with measure definitions, data sources, timeline, and responsible individuals should be recorded in the respective columns. When possible, provide updates related to progress or notes relevant to the implementation of the strategy. This worksheet is a suggested template, which can be modified as needed, and can be submitted as Section V in the Integrated Plan submission. This worksheet can also be used as a "living document" to assist in achieving the steps outlined in Section VI: Integrated Planning Implementation, Monitoring, and Jurisdictional Follow-Up.
Goal #:
Overarching statement that describes what the jurisdiction aims to achieve in response to identified needs. Integrated Plan goals are aligned with national priorities (Diagnose, Treat, Prevent, Respond).
Objective | Strategy | EHE Strategy | Performance Measure | Measure Definition | Baseline Year | Baseline Value | Timeline | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
Objectives are specific, measurable, achievable, relevant, and time-bound targets that facilitate progress toward meeting the overall goal. Multiple objectives may be needed to meet a goal. | Describes a specific activity related to an objective that a particular program, agency, or other entitity implements to support achievement of its related objective. Objectives often require multiple strategies. | Identify corresponding EHE strategy (i.e., Diagnose, Treat, Prevent, Respond) | Details a specific and measurable task, activity, or data point that operationalizes the objective. | Numerical value, product, or meeting convening demonstrating outcomes related to the activity. | The initial year for which future progress/ outcomes will be measured against. | The initial value for which future progress/ outcomes will be measured against. | Time frame to reach identified performance measure. | Where the data to calculate the measure or outcome are tracked/stored. | Key partners involved in data collection and/or service delivery. | Office or position overseeing the collection and/or reporting of data related to the activity. | Office or position overseeing the execution/ coordination of the activity. | Current state of the activity; identify any implementation barriers. | Detail information relevant to the implementation of the activity. | Details progress on activity as it relates to the overall objective; include numerical values and concrete outcomes when possible.

## IP WP & Monitoring Example
EXAMPLE: Integrated HIV and Prevention and Care Plan Work Plan and Monitoring Table, 2027-2031
Example Goal 1: Diagnose all people with HIV as early as possible.
Objective / Strategy # | Objective / Strategy | EHE Strategy | Performance Measure | Measure Definition | Baseline Year | Baseline Value | Timeline | Data Source | Implementing Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
Example Objective 1.1 | By December 31, 2031, increase the annual number of HIV tests conducted by DPH-funded providers by 10% from [X] to [X]. | Diagnose | # of HIV tests | # of HIV rapid tests distributed, # of HIV testing encounters by funded providers | 2026 | [X] | 1931-12-31 | DPH testing data | HIV Prevention Program | Infectious Disease Epi | HIV Program Manager
Example Strategy 1.1.a | Train 80% of funded HIV testing providers (n=X) in rapid test protocol and results interpretation. | Diagnose | # of providers trained |  | 2026 | [X] | 2029-01-01 | Epi database | Infectious Disease Training Division | Infectious Disease Training Division | HIV Program Manager
Strategy 1.1.b
Strategy 1.1.c
Objective 1.2
Strategy 1.2.a
Strategy 1.1.b
Strategy 1.1.c
Example Goal 2: Treat HIV timely and effectively.
Objective / Strategy # | Objective / Strategy | EHE Strategy | Performance Measure | Measure Definition | Baseline Year | Baseline Value | Timeline | Data Source | Implementing Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
Example Objective 2.1 | By January 1, 2030, increase the total number of people with HIV in [jurisdiction] who are engaged in care from 85% [n=X] to 90% [n=X]. | Treat | # of people with HIV who are engaged in care | # of individuals individuals with HIV with a reported ≥1 VL or CD4 test result within the last 12 months | 2026 | [X] | 1930-01-01 | eHARS | RWHAP Part A recipient, RWHAP Part B recipient, EHE recipient | HIV Surveillance Team | HIV Surveillance Team
Example Strategy 2.1.a | Increase the number of DPH-funded health centers providing HIV Rapid Start antiretroviral therapy as the standard of care by 10% (from [X] to [X]). | Treat | # of health centers implementing HIV Rapid Start ART | Rapid Start defined as initiating ART within 72 hours of diagnosis | 2026 | [X] | 1930-01-01 | CAREWare ID program report | Health center providers | Infectious Disease Epi | HIV Program Manager
Strategy 2.1.b
Strategy 2.1.c
Objective 2.2
Strategy 2.2.a
Strategy 2.2.b
Strategy 2.2.c
Example Goal 3: Prevent new HIV transmissions.
Objective / Strategy # | Objective / Strategy | EHE Strategy | Performance Measure | Measure Definition | Baseline Year | Baseline Value | Timeline | Data Source | Implementing Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
Example Objective 3.1 | By December 31, 2031, increase the total number of individuals using PrEP within the jurisdiction by 10% from [X] to [X]. | Prevent | # of individuals using PrEP | # of individuals using PrEP within the jurisdiction | 2026 | [X] | 1931-12-31 | PrEPVu - IQVIA database | Health centers, DPH-funded providers | Infectious Disease Epi | HIV Program Manager
Example Strategy 3.1.a | Increase the number of DPH-funded health centers implementing a same-day PrEP initiation protocol by 15% (from [X] to [X]). | Prevent | # of health centers | Health centers implementing same-day PrEP initiation protocol | 2026 | [X] | 2030-01-01 | ID program report | Health centers | Infectious Disease Epi | HIV Program Manager
Strategy 3.1.b
Strategy 3.1.c
Objective 3.2
Strategy 3.2.a
Strategy 3.2.b
Strategy 3.2.c
Example Goal 4: Respond quickly to potential HIV clusters and/or outbreaks.
Objective / Strategy # | Objective / Strategy | EHE Strategy | Performance Measure | Measure Definition | Baseline Year | Baseline Value | Timeline | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
Example Objective 4.1 | Begining in January 2027 and anually thereafter, the Division of HIV Surveillance will coordinate a meeting with the RWHAP Part B HIV Planning Group and RWHAP Part A HIV Planning Council to review and solicit feedback on the Cluster and Outbreak Detection and Response (CDR) Plan and disseminate findings. | Respond | # and dates of planning body meetings on HIV cluster detection and response held; date findings were circulated | Dates planning body meetings held to discuss CDR; date findings/updates based on discussions were disseminated to planning body members | 2027 | - | Annually, by 12/31 each year | Planning body agendas/ minutes; CDR Plan | HIV Prevention Program Manager, HIV Care Program Manager, PC Support Staff, CDR Committee |  | HIV Prevention Program Manager HIV Care Program Manager
Example Strategy 4.1.a | Increase community understanding of cluster detection activities by presenting at community engagement events/meetings. | Respond | # and dates of community events/presentations | # and dates of presentations on cluster detection activities presented at community events | 2027 | - | Annually, by 12/31 each year | CDR monitoring plan | HIV Prevention Program Manager, CDR Committee
Strategy 4.1.b
Strategy 4.1.c
Objective 4.2
Strategy 4.2.a
Strategy 4.2.b
Strategy 4.2.c

## IP WP & Monitoring Template
Integrated HIV and Prevention and Care Plan Work Plan and Monitoring Table, 2027-2031
Goal 1:
Objective / Strategy # | Objective / Strategy | EHE Strategy | Performance Measure | Measure Definition | Baseline Year | Baseline Value | Timeline | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
Objective 1.1
Strategy 1.1.a
Strategy 1.1.b
Strategy 1.1.c
Objective 1.2
Strategy 1.2.a
Strategy 1.2.b
Strategy 1.2.c
Objective 1.3
Strategy 1.3.a
Strategy 1.3.b
Strategy 1.3.c
Goal 2:
Objective / Strategy # | Objective / Strategy | EHE Strategy | Performance Measure | Measure Definition | Baseline Year | Baseline Value | Timeline | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
Objective 2.1
Strategy 2.1.a
Strategy 2.1.b
Strategy 2.1.c
Objective 2.2
Strategy 2.2.a
Strategy 2.2.b
Strategy 2.2.c
Objective 2.3
Strategy 2.3.a
Strategy 2.3.b
Strategy 2.3.c
Goal 3:
Objective / Strategy # | Objective / Strategy | EHE Strategy | Performance Measure | Measure Definition | Baseline Year | Baseline Value | Timeline | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
Objective 3.1
Strategy 3.1.a
Strategy 3.1.b
Strategy 3.1.c
Objective 3.2
Strategy 3.2.a
Strategy 3.2.b
Strategy 3.2.c
Objective 3.3
Strategy 3.3.a
Strategy 3.3.b
Strategy 3.3.c
Goal 4:
Objective / Strategy # | Objective / Strategy | EHE Strategy | Performance Measure | Measure Definition | Baseline Year | Baseline Value | Timeline | Data Source | Responsible Parties | Responsible Data Staff | Responsible Program Staff | Status | Notes | Progress Notes
Objective 4.1
Strategy 4.1.a
Strategy 4.1.b
Strategy 4.1.c
Objective 4.2
Strategy 4.2.a
Strategy 4.2.b
Strategy 4.2.c
Objective 4.3
Strategy 4.3.a
Strategy 4.3.b
Strategy 4.3.c